## Sheet1
Sprint Backlog | Iteration
Project
Group | 43
Amount of hours
Member | Daan | Sem | Merel | Ceren | Mika
Estimated amount of hours | 6 | 5
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)
Research | get to know the used programs | All | All | 2 | B
Create barebone structure Client-Server connection | <- | Ceren | Ceren | 2 | A
Setup github | Update gitignore | Sem | Sem | 0.5 | C
Setup github | Check git config settings | Merel | Merel | 0.5 | C
Setup github | Update a project to git to work from | Daan | Daan | 0.5 | A
Setup scrum board | Fill in scrum board | Merel | Merel | 0.5 | B
Setup scrum board | Add description for issues | Daan | Daan | 0.5 | C
Setup github | Add license | Sem | Sem | 0.5 | C
Create a score schema | <- | Mika | Mika | 1 | C
Research | Get acquainted with JavaFX | Sem+Mika | Sem+Mika | 4 | B
Research | Manage Design Database | Daan | Daan | 1 | B
Research | Research database options | Daan+Merel | Daan+Merel | 4 | B
Research | Figuring out how CI works | Ceren | Ceren | 0.5 | C
User login | User can register | Ceren | Ceren | 6 | B
User login | Configure basic authentication | Ceren | Ceren | 1.5 | B