## Sheet1
Sprint Retrospective | Iteration
Project
Group | 43
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
Research | get to know the used programs | All | All | 2 | yes
Create barebone structure Client-Server connection | <- | Ceren | Ceren | ? | yes
Setup github | Update gitignore | Sem | Sem | 0.5 | yes
Setup github | Check git config settings | Merel | Merel | 0.5 | yes
Setup github | Update a project to git to work from | Daan | Daan | ? | yes
Setup scrum board | Fill in scrum board | Merel | Merel | 0.5 | yes
Setup scrum board | Add description for issues | Daan | Daan | 0.5 | yes
Setup github | Add license | Sem | Sem | 0.5 | yes
Create a score schema | <- | Mika | Mika | 1 | yes
Research | Get acquainted with JavaFX | Sem+Mika | Sem+Mika | 4 | yes
Research | Manage Design Database | Daan | Daan | ? | yes
Research | Research database options | Daan+Merel | Daan+Merel | ? | yes
Research | Figuring out how CI works | Ceren | Ceren | ? | yes
User login | User can register | Ceren | Ceren | ? | yes
User login | Configure basic authentication | Ceren | Ceren | ? | yes
Main Problems Encountered
Problem 1
Description
Reaction
Problem 2
Description
Reactions
Adjustments for next Sprint Plan
Make the plan before the week is over